Project Planning Phase

Module 1: Product Backlog, Sprint Planning & Estimation

| ## Date : | ## 13.10.2026 |
| --- | --- |
| ## Team ID : | ## SWTID-2026-8782 |
| ## Project Name : | ## Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designer |

# 1. Product Backlog

The product backlog lists the user stories required to deliver the automated Standard Laptop procurement workflow in ServiceNow, prioritised by business value.

| ID | User Story | Priority | Story Points | Owner |
| --- | --- | --- | --- | --- |
| USN-1 | As an employee, I can open the Standard Laptop catalog item and submit a request so that I do not need to email IT. | High | 3 | Srilekha B |
| USN-2 | As a manager, I receive an approval request for a laptop order so that I can approve or reject it. | High | 3 | Sheela Rani B |
| USN-3 | As the system, I automatically start the Standard Laptop Task flow once the request is approved. | High | 5 | Srilekha B |
| USN-4 | As the system, I automatically create a Catalog Task and assign it to the Hardware Assignment Group. | High | 5 | Hemalatha K |
| USN-5 | As a hardware team member, I can see the assigned task and update its status while processing the laptop. | Medium | 3 | Anbarasi S |
| USN-6 | As an employee, I can track the status of my request until completion. | Medium | 2 | Sheela Rani B |
| USN-7 | As an administrator, I can view flow execution details to identify workflow issues. | Low | 2 | Hemalatha K |
| USN-8 | As a team, we test the end-to-end flow and document the results. | Medium | 3 | Anbarasi S |

# 2. Sprint Planning

The work is divided into three one-week sprints.

| Sprint | Goal | User Stories | Total Story Points | Start Date | End Date |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Set up catalog item and approval | USN-1, USN-2 | 6 | 28.09.2026 | 03.10.2026 |
| Sprint-2 | Build Flow Designer automation and task assignment | USN-3, USN-4, USN-5 | 13 | 05.10.2026 | 10.10.2026 |
| Sprint-3 | Status tracking, monitoring, testing and documentation | USN-6, USN-7, USN-8 | 7 | 12.10.2026 | 17.10.2026 |

# 3. Estimation & Velocity

Estimation uses story points on a Fibonacci-style scale (1, 2, 3, 5).

Total backlog size is 26 story points across 3 sprints.

Average velocity = 26 story points / 3 sprints ≈ 8.7 story points per sprint.

Team size is 4 members: Srilekha B (Team Leader), Sheela Rani B, Hemalatha K and Anbarasi S.

# 4. Sprint Delivery Schedule

| Sprint | Planned Points | Sprint Duration | Planned Release |
| --- | --- | --- | --- |
| Sprint-1 | 6 | 6 days | 03.10.2026 |
| Sprint-2 | 13 | 6 days | 10.10.2026 |
| Sprint-3 | 7 | 6 days | 17.10.2026 |